## Sheet1
Water and Cleanliness Management Portal
Daily Updates from 15th August to 20th December
15th August 2020 | 18th August | 22th August | 27th August | 3rd September | 10th September | 17th september | 22th September | 30th September | 5th October | 11th October
Decided the topic and domain which we have targeted. | Researched about the domain which we have targetted its future challenges and outcome. | Communicated with the stake holders and there problems. | A meeting was there with the Nagarpalika officers. | Decided what to add in the portal like features, designs and all that. | Choosed the templates from admin side as well as from user side. | Started working on the portal and research work. | Divided the work into two parts, like user side was from krupal side and admin side was handled by karan. | Started adding the features from both side. | Added some features like included the google calender in admin side and tried some color combinations. | working on same things from both side
13th October | 23th October | 27th October | 2nd November | 10th November | 19th November | 27th November | 3rd December | 10th December | 15th December | 20th December
Had meeting with parmar sir regarding the topic and domina which we have selected. | Discussed the color combinations and designs with Mr. Aravind srinivasan. | Edited the color combinations that have been told by Mr. Aravind | Started exploring about php and its working. | Same work done and some progress in the project | Done with the hardware part interfacing the sensors and further process | Done with the E-R diagrams and further known about the connection and all that | Had a meeting with the Nagarpalika officers regarding this. | Done with the viva process and other project work, updated the E-R Diagram | Further Re-designed and some addition of files like complain domain and other features. | Finally the portal is done as per our work, follow up by side, like karan has verified by my side, and I have verified from karan side that is from admin side.
In between this dates we have Communicated with the stakeholders, Krunal sir and Parmar sir and solved our doubts.